## Sheet1
| Task | Responsible Unit | Status | Comment
1 | First team meeting "Who is Who” in Facebook | all | done | contacted: Iliya Iliev, Petar Uzunov, Mar123456, Todor Peshin.Lubomir Goychev,HristoBahnev
2 | Create a GitHub repository | Petar Uzunov | done | https://github.com/PeUzunov/QA-Automation-Team-Project
3 | Create a GitHub acconts and add to repository | all | in progress | PeUzunov, lgoychev, hbahnev
4 | Download and research the team project (blog) | all
5 | Research for best SRS templates or examples which are best fit to the project
6 | Research for best Use cases templates or examples which are best fit to the project
7 | Research for best Test scenarios templates or examples which are best fit to the project
8 | Research for best way to implement atomation tests with Selenium IDE
9 | Write a SRS document.
10 | Write a Testplan for functionality test.
11 | Write test scenarios with test case
12 | Create Selenium WebDriver test framework
13 | Build Continuous Integration with TeamCity
14 | Start to create automation tests according to TestPlan
15 | Add defect into bug-tracking system (github)
16 | Check and prepare tests for next release of the blog
17 | Execute tests for new release (0.2)
18 | Add defect into bug-tracking system (github)
19 | Create additional atomation tests according to new functionality of ver. 0.2
20 | Check and prepare tests for next release
21 | Design and write a presentation of the project for team defence
22 | Preparing all documents and apllication for presentation.
23 | Preliminary presentation of the project
24 | Final Presentation of the project